## Sheet1
| SecondHand.com | Project Objective: | To create a classified website like the popular ones in the market Eg: OLX, Quikr
Team Size | 3
Team Memebers | Flora Moses | Project Introduction | SecondHand.com acts as a interface between buyer and seller
Pranavi Dandu
| Naga Purnika | Project Architecture | MVC Architecture
| First task | Setup Bitbucket Repository | Team Work | INIT project template in repository with basic infrastructure like DB support, Authentication filter, index page, session timeout, etc. Assign write role to entire team. Team started working on project by checking out project in local Eclipse
Date | Functionaliy No | Functionality | Owner | DB Design | DAO Classes | Entities/Bean | View Pages | Controllers(Servlets)
11th June | 1 | Login Functionlity | Flora Moses | Register Table | UserDAO | UserBean | login.jsp | LoginController
| 2 | Welcome Page | Naga Purnika | - | - | - | start.jsp | -
| 3 | LogoutFuntionality | Pranavi Dandu | Register Table | UserDAO | UserBean | login.jsp | LogoutController
12th June |  | Signup Functionality | Team Work | Register Table | UserDAO | UserBean | signup.jsp | SignUpController
13th June |  | Search Funtionality | Team Work | Search Table | SearchDAO | SearchBean | start.jsp | SearchController
15th June |  | SubmitAnAd Functionality | Team Work | SubmitAnAd Table | SubmitAnAdDAO | SubmitAnAdBean | submit.jsp | SubmitAnAdController
16th June |  | All the UI | Team Work | - | - | - | start.jsp | -
17th June |  | ViewingAnAd | Pranavi Dandu | SubmitAnAd Table | SubmitAnAdDAO | SubmitAnAdBean | show.jsp | SubmitAnAdController